## Evidence
ID | Type | Reference | Area | What the auditor will ask | Evidence to show | Where it is kept | Owner | How often | Evidence status | Linked risks | Ready by | Notes
E01 | ISO 27001 clause | Clause 4.3 | ISMS scope | What is inside and outside the ISMS, and why? | isms-scope.md | Repo: 01-scope-policy | ISMS Manager | On change, reviewed yearly | In repo |  | Done
E02 | ISO 27001 clause | Clause 5.2 | Information security policy | Is there an approved policy, and do staff know about it? | information-security-policy.md signed by the CEO; staff acknowledgement at onboarding | Repo: 01-scope-policy; HR folder | ISMS Manager | Yearly | Partly in place |  | 2027-01-17 | Policy approved. Staff acknowledgement list still missing.
E03 | ISO 27001 clause | Clause 5.3 | Roles and responsibilities | Who is the ISMS Manager, and who owns each risk? | Role description signed by the CEO; risk owners named in the register | Repo: 02-risk; HR folder | CEO | On change | Partly in place |  | 2027-01-17 | Owners are named in the register. Signed role description missing.
E04 | ISO 27001 clause | Clause 6.1.2 | Risk assessment method | How do you identify and rate risks? | risk-assessment-method.md (5x5 scale, thresholds, due dates) | Repo: 02-risk | ISMS Manager | Yearly | In repo |  | Done
E05 | ISO 27001 clause | Clause 6.1.2 | Risk assessment results | Show the results and when they were last reviewed. | risk-register.xlsx (30 risks); yearly review record | Repo: 02-risk | ISMS Manager | Yearly | In repo |  | Done | Add a dated review note at each yearly review.
E06 | ISO 27001 clause | Clause 6.1.3 | Risk treatment plan | What will you do about each risk, who owns it, and by when? | Treatment, planned control, owner and due date columns in the risk register | Repo: 02-risk | ISMS Manager | Quarterly progress check | In repo |  | Done
E07 | ISO 27001 clause | Clause 6.1.3 | Statement of Applicability | Which controls apply, and why are others excluded? | statement-of-applicability.xlsx (93 controls with reasons) | Repo: 03-controls | ISMS Manager | Yearly | In repo |  | Done
E08 | ISO 27001 clause | Clause 6.2 | Security objectives | What are your objectives, and how do you track them? | Objectives in the policy; quarterly progress note per objective | Repo: 01-scope-policy; SharePoint | ISMS Manager | Quarterly | Partly in place |  | 2027-01-31 | Objectives exist. Progress tracking starts with the first quarterly report.
E09 | ISO 27001 clause | Clause 7.2 | Competence | Is the ISMS Manager trained for the role? | Training or certificate records for the ISMS Manager | HR folder | CEO | On change | To create |  | 2027-04-19 | Needs training or an ISO 27001 course for the part-time IT administrator.
E10 | ISO 27001 clause | Clause 7.5 | Document control | How are documents versioned, approved and kept current? | Version numbers, approval lines and Git history; list of ISMS documents | Repo (Git history) | ISMS Manager | On change | Partly in place |  | 2027-01-17 | Git history exists. Add a document list to the README.
E11 | ISO 27001 clause | Clause 9.1 | Monitoring and measurement | How do you know the ISMS works? | Quarterly report: open risks by level, MFA coverage, training completion, patch compliance, incidents | SharePoint: ISMS reports | ISMS Manager | Quarterly | To create |  | 2027-01-31
E12 | ISO 27001 clause | Clause 9.2 | Internal audit | Show the audit programme and the last internal audit report. | Audit plan, report with findings, follow-up actions | SharePoint: ISMS audit | ISMS Manager | Yearly, before certification | To create |  | 2027-06-30 | Independent person needed. Consider an external consultant.
E13 | ISO 27001 clause | Clause 9.3 | Management review | Show the minutes of the last management review. | Minutes with inputs (risks, incidents, audit results) and decisions | SharePoint: ISMS reports | CEO | Yearly | To create |  | 2027-07-31
E14 | ISO 27001 clause | Clause 10.2 | Nonconformities and corrective action | How do you record and fix problems? | Log of findings, causes, actions, owners and closure dates | SharePoint: ISMS reports | ISMS Manager | Ongoing | To create |  | 2027-01-31
E15 | Annex A control | 5.15; 5.18 | Access reviews | Show the last quarterly access review for Azure, GitHub and the database. | Signed review sheet: accounts, roles, changes made, reviewer, date | SharePoint: ISMS evidence | Head of Engineering | Quarterly | To create | R02, R07, R13, R26 | 2026-11-18
E16 | Annex A control | 5.16; 6.5 | Joiner, mover, leaver | Show the checklists for the last three leavers. | Completed leaver checklists with dates; Entra ID audit log showing the account disabled | HR folder; Entra ID | Head of Operations | Per leaver | To create | R07, R13 | 2027-01-17 | Checklist must also cover GitHub, Azure and the support tool (R13).
E17 | Annex A control | 8.5 | Multi-factor authentication | How many accounts use MFA, and can any account skip it? | Entra ID authentication methods report; Conditional Access policy screenshot | Entra ID | IT Administrator | Monthly | Partly in place | R01, R02, R12, R17 | 2026-11-18 | MFA is on email for some staff only today.
E18 | Annex A control | 8.2; 5.3 | Privileged access | Who are the administrators, and how do they sign in? | Admin role list; passkey or security key registration; break-glass account test record | Entra ID; Azure | Head of Engineering | Quarterly | To create | R02, R10, R30 | 2026-11-18 | Also covers R10, the single point of failure.
E19 | Annex A control | 5.17 | Passwords | How are passwords managed? | Password manager rollout record; Entra ID password policy settings | Password manager; Entra ID | IT Administrator | Yearly | Partly in place | R01, R17 | 2027-01-17
E20 | Annex A control | 8.3; 8.20 | Database access | Who can reach customer data, and from where? | Azure SQL network settings (private endpoints), role assignments, quarterly configuration review | Azure | Head of Engineering | Quarterly | To create | R03, R20, R26, R30 | 2026-11-18
E21 | Annex A control | 8.4; 8.28 | Source code protection | How do you stop secrets and unreviewed code reaching production? | GitHub settings: branch protection, required review, secret scanning, push protection, SSO and MFA | GitHub | Head of Engineering | Quarterly | To create | R11, R12, R29 | 2027-01-17
E22 | Annex A control | 6.3 | Security awareness training | Show who was trained and how phishing tests went. | Attendance list; phishing simulation results; onboarding checklist | SharePoint: ISMS evidence | ISMS Manager | Yearly | To create | R01, R19, R21 | 2026-11-18 | Training is the main fix for the top risk, phishing.
E23 | Annex A control | 6.8; 5.24 | Incident reporting | How do staff report incidents, and show the incident log. | Reporting channel and mailbox; incident log (or a statement that none occurred) | Teams; SharePoint | ISMS Manager | Ongoing | To create | R19, R23, R24 | 2027-01-17
E24 | Annex A control | 5.25; 5.26; 5.27 | Incident exercise | Have you practised the response? | Tabletop exercise report with actions and owners | SharePoint: ISMS evidence | ISMS Manager | Yearly | To create | R23 | 2027-01-17 | First exercise by 17 January 2027 (see the incident response policy).
E25 | Annex A control | 8.15; 8.16 | Logging and alerts | What is logged, for how long, and who looks at alerts? | Defender for Cloud settings; log retention configuration; a sample alert and response | Azure | Head of Engineering | Quarterly | Partly in place | R14, R30 | 2027-01-17 | Only basic Azure activity logs today.
E26 | Annex A control | 8.13; 5.30 | Backup and restore | Have you tested that you can restore? | Restore test report with time taken against the recovery targets | Azure; SharePoint | Head of Engineering | Quarterly | To create | R08, R16, R30 | 2027-01-17
E27 | Annex A control | 8.8; 8.7 | Patching and malware protection | How quickly are critical updates installed, and is protection active? | Patch compliance report (14-day target); Defender coverage report | Device management | IT Administrator | Monthly | Partly in place | R04, R29, R30 | 2027-01-17
E28 | Annex A control | 8.1; 8.24 | Devices and encryption | Are laptops encrypted and phones protected? | Device compliance report: disk encryption, screen lock; app protection policy for work email on phones | Intune or device management | IT Administrator | Quarterly | To create | R04, R05, R06, R20, R27 | 2027-01-17 | Also covers R05, lost or stolen laptops.
E29 | Annex A control | 5.19; 5.22 | Suppliers | Show the supplier register and the checks on key suppliers. | Supplier register; security reviews for the payment, support and backup suppliers; data processing agreements | SharePoint: ISMS evidence | ISMS Manager | Yearly | To create | R09 | 2027-04-19
E30 | Annex A control | 5.34; 5.31 | GDPR records | Show your record of processing and how requests are handled. | Record of processing activities; data subject request log with 30-day tracking; data processing agreements | SharePoint: privacy | Head of Operations | Ongoing | To create | R03, R22, R23, R24, R25, R26 | 2027-04-19
E31 | Annex A control | 5.31 | NIS2 applicability | Does NIS2 apply to you, and how did you decide? | Written applicability assessment with the conclusion and date | SharePoint: ISMS evidence | ISMS Manager | Yearly | To create | R22, R23, R24, R25 | 2027-01-17
E32 | Annex A control | 5.9 | Asset inventory | Show the list of your information assets. | Inventory of systems, data and devices with owners | SharePoint: ISMS evidence | IT Administrator | Yearly | To create |  | 2027-01-17 | Assets are in the risk register only today.
E33 | Annex A control | 5.10; 6.7 | Acceptable use and remote working | What rules do staff follow, and did they accept them? | Published rules; staff acknowledgement list | SharePoint; HR folder | ISMS Manager | Yearly | To create | R06, R18, R20, R21 | 2027-04-19
E34 | Annex A control | 6.2 | Employment terms | Do contracts state security duties? | Contract template with confidentiality and security clauses | HR folder | Head of Operations | On change | Partly in place |  | 2027-04-19 | Contracts exist. Security duties are not yet explicit.
E35 | Annex A control | 7.2 | Office access | Who can enter the office, and how are visitors recorded? | Visitor sign-in sheet; key list; quarterly review | Office | Head of Operations | Quarterly | To create | R28 | 2027-01-19

## Summary
Evidence status | Count
In repo | 5
Partly in place | 9
To create | 21
Total | 35
Evidence status by owner | In repo | Partly in place | To create
CEO | 0 | 1 | 2
Head of Engineering | 0 | 1 | 5
Head of Operations | 0 | 1 | 3
ISMS Manager | 5 | 3 | 9
IT Administrator | 0 | 3 | 2

## How to use
Audit evidence checklist: Havelmetrics GmbH
What this is: a list of the proof an ISO 27001 auditor would ask to see, so the company can be ready before the audit.
Each row has a question the auditor will ask, the evidence that answers it, where it is kept, who owns it, and when it should be ready.
Evidence status:
In repo: the document already exists in this project.
Partly in place: something exists, but the proof is incomplete.
To create: the evidence will only exist once the control is running. Records such as reviews, test reports and logs are produced on a schedule.
How the rows connect to the rest of the project:
Annex A control rows use the control numbers from the Statement of Applicability (03-controls). Linked risks come from the same file.
Ready by dates for control rows are the due dates of the main risk in the risk register (02-risk). Clause rows use dates set for the first certification audit.
The policies in 04-policies set the rules. This checklist lists the records that show the rules are followed.
Suggested evidence folder (SharePoint): ISMS evidence / year / area (for example 2027 / access reviews / Q1 review).
Keep one file per record, named with the date, and never delete old records.