## Risk Register
ID | Asset | Threat | Vulnerability | Likelihood | Impact | Score | Level | Existing controls | Treatment | Planned control | Owner | Due date | Status
R01 | Microsoft 365 and Entra ID accounts | Phishing leads to account takeover | Staff not trained to spot phishing; MFA only partly enforced | 4 | 4 | 16 | Critical | Spam filtering in Microsoft 365; MFA on email for some staff | Reduce | Enforce MFA for all accounts, passkeys for administrators, annual phishing awareness training | ISMS Manager | 2026-11-18 | In progress
R02 | Azure production environment | Administrator account compromised | Not all admin accounts use MFA or passkeys; admin rights are broad | 3 | 5 | 15 | Critical | Sign-in through Entra ID | Reduce | Require passkeys or hardware security keys for all admins; apply role-based access and least privilege | Head of Engineering | 2026-11-18 | Open
R03 | Azure SQL customer database | Customer data exposed | Network access and firewall settings not reviewed regularly | 3 | 5 | 15 | Critical | Encryption at rest (Azure default) | Reduce | Restrict access to private endpoints only; quarterly review of database configuration | Head of Engineering | 2026-11-18 | Open
R04 | Company laptops | Malware through unpatched software | No documented patch process or deadline | 4 | 3 | 12 | High | Automatic Windows updates (not monitored) | Reduce | Define 14-day patch deadline for critical updates and monitor compliance through device management | IT Administrator | 2027-01-17 | Open
R05 | Company laptops | Lost or stolen device exposes data | Disk encryption exists but is not enforced or verified | 3 | 3 | 9 | Medium | Disk encryption on most laptops | Reduce | Enforce and verify disk encryption on every laptop; enable remote wipe | IT Administrator | 2027-04-19 | Open
R06 | Personal phones used for email | Company email data leaks from unmanaged phones | No device management, screen lock or app protection rules | 4 | 3 | 12 | High | None | Reduce | Require app protection policy for work email (Microsoft Intune) or restrict email to managed apps | IT Administrator | 2027-01-17 | Open
R07 | Microsoft 365 and Entra ID accounts | Leavers keep access after departure | No documented joiner, mover and leaver process | 3 | 4 | 12 | High | IT administrator removes access when told, with no set deadline | Reduce | Documented leaver checklist agreed with management; access removed on the last working day | Head of Operations | 2027-01-17 | Open
R08 | Backups | Data cannot be restored after an incident | Backups are never tested | 3 | 4 | 12 | High | Backup service in place | Reduce | Quarterly restore test; document recovery time and recovery point targets | Head of Engineering | 2027-01-17 | Open
R09 | Suppliers (payment, support tool, backup service) | Supplier outage or breach affects customers | No supplier security review or register | 2 | 3 | 6 | Medium | Standard contract terms | Reduce | Create supplier register; review security documents and data processing agreements for the three key suppliers | ISMS Manager | 2027-04-19 | Open
R10 | IT administrator role | Single point of failure | One part-time person holds all administration knowledge | 3 | 3 | 9 | Medium | None | Reduce | Document admin procedures; give a second trusted person emergency (break-glass) access | CEO | 2027-04-19 | Open
R11 | GitHub source code repositories | Secrets such as keys or passwords leaked in code | No secret scanning or push protection | 3 | 4 | 12 | High | Repositories are private | Reduce | Enable secret scanning and push protection; rotate any secret found | Head of Engineering | 2027-01-17 | Open
R12 | GitHub source code repositories | Developer account compromised | MFA not enforced for every organisation member | 3 | 4 | 12 | High | Repositories are private | Reduce | Enforce MFA and single sign-on through Entra ID; require branch protection and code review | Head of Engineering | 2027-01-17 | Open
R13 | GitHub source code repositories | Leaver copies or keeps source code access | GitHub is not part of the leaver checklist | 2 | 3 | 6 | Medium | None | Reduce | Add GitHub, Azure and support tool to the leaver checklist (see R07) | Head of Engineering | 2027-04-19 | Open
R14 | Azure production environment | Attack goes unnoticed | No central logging, alerting or defined log retention | 4 | 3 | 12 | High | Basic Azure activity logs | Reduce | Enable Microsoft Defender for Cloud and central logging with alerts; define log retention | Head of Engineering | 2027-01-17 | Open
R15 | Azure test environment | Real customer data exposed through testing | Production data is sometimes copied into the test environment | 3 | 4 | 12 | High | None | Reduce | Prohibit production data in test; use anonymised test data | Head of Engineering | 2027-01-17 | Open
R16 | Azure production environment | Service outage lasting longer than customers accept | Single-region setup; failover never tested | 2 | 4 | 8 | Medium | Azure platform service levels | Reduce | Define recovery targets; test failover plan or formally accept the risk with a documented reason | Head of Engineering | 2027-04-19 | Open
R17 | Staff accounts | Weak or reused passwords | No password manager; passwords still used alongside MFA | 4 | 3 | 12 | High | Minimum password length set in Entra ID | Reduce | Roll out a company password manager; move staff towards passkeys | IT Administrator | 2027-01-17 | Open
R18 | Microsoft 365 files and email | Sensitive data shared with the wrong people | External sharing is unrestricted; no data labels | 3 | 3 | 9 | Medium | None | Reduce | Restrict external sharing to approved domains; introduce sensitivity labels for customer data | IT Administrator | 2027-04-19 | Open
R19 | Staff | Security incidents not reported or reported late | No known reporting channel; staff unsure what counts as an incident | 3 | 3 | 9 | Medium | None | Reduce | Set up an incident reporting channel and include it in onboarding and annual training | ISMS Manager | 2027-04-19 | Open
R20 | Remote work | Data intercepted on home or public networks | No remote working rules; no VPN or conditional access | 3 | 3 | 9 | Medium | HTTPS used for cloud services | Reduce | Publish remote working rules; enforce device firewall and conditional access for company data | IT Administrator | 2027-04-19 | Open
R21 | Remote work | Screens or devices seen or used by others at home | No guidance on locking screens or shared home devices | 2 | 2 | 4 | Low | None | Accept | No new control now; include screen-lock guidance in training and review each quarter | ISMS Manager | 2027-01-19 | Open
R22 | Customer personal data (GDPR) | Data subject requests handled late or wrongly | No documented process or tracking for access and deletion requests | 3 | 3 | 9 | Medium | Requests handled by email without a process | Reduce | Document request process with 30-day tracking and a named owner | Head of Operations | 2027-04-19 | Open
R23 | Incident response (GDPR) | Personal data breach not reported to the authority within 72 hours | No incident response plan or decision process | 3 | 4 | 12 | High | None | Reduce | Create incident response policy with severity levels, a 72-hour breach decision checklist and contact details | ISMS Manager | 2027-01-17 | Open
R24 | Regulatory compliance (NIS2) | Incident reporting duties missed | Havelmetrics has not assessed whether NIS2 applies to it as a supplier | 3 | 4 | 12 | High | None | Reduce | Complete NIS2 applicability assessment; align incident procedure with early warning (24 hours) and notification (72 hours) timelines | ISMS Manager | 2027-01-17 | Open
R25 | Customer security questionnaires | Inconsistent or inaccurate answers to customers | Answers are written ad hoc by different people | 4 | 2 | 8 | Medium | None | Reduce | Maintain one approved answer library reviewed by the ISMS Manager | Head of Sales and Support | 2027-04-19 | Open
R26 | Customer support tool | Customer data exposed through support tickets | Broad staff access; sensitive data kept in tickets without retention limits | 3 | 3 | 9 | Medium | Login required for the support tool | Reduce | Role-based access; retention limits; mask sensitive data in tickets | Head of Sales and Support | 2027-04-19 | Open
R27 | Payment provider integration | Payment-related keys or data compromised | Integration keys stored in configuration files | 2 | 4 | 8 | Medium | Provider handles card data on its own platform (assumed) | Reduce | Store keys in Azure Key Vault and rotate them regularly | Head of Engineering | 2027-04-19 | Open
R28 | Berlin office (Kreuzberg) | Unauthorised physical access | No visitor sign-in; keys not tracked | 2 | 2 | 4 | Low | Locked door with key access | Accept | Add a visitor sign-in sheet and key list; review each quarter | Head of Operations | 2027-01-19 | Open
R29 | Product software dependencies | Known vulnerabilities in third-party libraries | No automated dependency scanning or update deadline | 4 | 3 | 12 | High | Developers update libraries occasionally | Reduce | Enable dependency scanning (for example Dependabot); define update deadlines by severity | Head of Engineering | 2027-01-17 | Open
R30 | Company laptops and Azure data | Ransomware encrypts systems and backups | Backups not isolated; endpoint protection not centrally monitored | 3 | 5 | 15 | Critical | Microsoft Defender antivirus on laptops | Reduce | Isolated or immutable backups; centrally monitored endpoint protection; least-privilege access | Head of Engineering | 2026-11-18 | Open